中华人民共和国湖南省审计厅

Hunan Provincial Audit Office of the People’s Republic of  China

审  计  报  告

Audit Report

湘审报〔2020〕33号

HUNAN AUDIT REPORT〔2020〕NO.33

项目名称：世界银行贷款湖南森林生态恢复和发展项目

Project Name: World Bank Loan- Hunan Forest Restoration and Development Project

贷款号：8215-CN

Loan No. 8215-CN

项目执行单位：湖南省林业外资项目管理办公室

Project Entity: Hunan Provincial Forestry Foreign Fund Project Management Office

会计年度：     2019年1月1日至2020年3月31日

Accounting Year：January 1, 2019—March 31, 2020

目    录

Contents

- 审计师意见………………………………………………………1

I. Auditor's Opinion

- 财务报表及财务报表说明

Ⅱ. Financial Statements and Notes to the Financial Statements

（一）资金平衡表…………………………………………………6

i.Balance Sheet

（二）项目进度表…………………………………………………8

ⅱ.Summary of Sources and Uses of Funds by Project Component

（三）贷款协定执行情况表………………………………………12

iii. Statement of Implementation of Loan Agreement

（四）专用帐户报表………………………………………………13

iv. Special Account Statement

（五）财务报表说明………………………………………………15

v.Notes to the Financial Statements

三、审计发现的问题及建议……………………………………………21

III. Audit Findings and Recommendations

一、审计师意见

审计师意见

湖南省林业外资项目管理办公室：

我们审计了世界银行贷款湖南森林生态恢复和发展项目2020年3月31日的资金平衡表及截至该日同年度的项目进度表、贷款协定执行情况表、专用帐户报表及财务报表说明（第6页至第20页）。

（一）项目执行单位及湖南省财政厅对财务报表的责任

编制上述财务报表中的资金平衡表、项目进度表及贷款协定执行情况表是你单位的责任，编制专用账户报表是湖南省财政厅的责任，这种责任包括：

1．按照中国的会计准则、会计制度和本项目贷款协定的要求编制项目财务报表，并使其实现公允反映；

2．设计、执行和维护必要的内部控制，以使项目财务报表不存在由于舞弊或错误而导致的重大错报。

（二）审计责任

我们的责任是在执行审计工作的基础上对财务报表发表审计意见。我们按照中国国家审计准则和国际审计准则的规定执行了审计工作，上述准则要求我们遵守审计职业要求，计划和执行审计工作以对项目财务报表是否不存在重大错报获取合理保证。

为获取有关财务报表金额和披露信息的有关证据，我们实施了必要的审计程序。我们运用职业判断选择审计程序，这些程序包括对由于舞弊或错误导致的财务报表重大错报风险的评估。在进行风险评估时，为了设计恰当的审计程序，我们考虑了与财务报表相关的内部控制，但目的并非对内部控制的有效性发表意见。审计工作还包括评价所选用会计政策的恰当性和作出会计估计的合理性，以及评价财务报表的总体列报。

我们相信，我们获取的审计证据是适当的、充分的，为发表审计意见提供了基础。

（三）审计意见

我们认为，第一段所列财务报表在所有重大方面按照中国的会计准则、会计制度和本项目贷款协定的要求编制，公允反映了世界银行贷款湖南森林生态恢复和发展项目 2019年12月31日及2020年1--3月的财务状况及截至该日同年度的财务收支、项目执行和专用账户收支情况。

本审计师意见之后，共同构成审计报告的还有两项内容：财务报表及财务报表说明和审计发现的问题及建议。

中华人民共和国湖南省审计厅

2020年6月24日

地址：中国湖南省长沙市嘉雨路6号

邮政编码：410001

电话：（0731）89976087

传真：（0731）89976085

I. Auditor’s Opinion

Auditor’s Opinion

To Hunan Provincial Forestry Foreign Fund Project Management Office:

We have audited the balance sheet of Hunan Forest Restoration and Development Project financed by the World Bank as of March 31, 2020, and the project progress sheet, the loan agreement implementation sheet, the special account statement and notes to the financial statements (from page 6 to page 20) up to the the date of the same year.

(I) Project entity and Hunan provincial finance department's responsibility for the financial statements

The preparation of the Balance Sheet, the Summary of Sources and Uses of Funds by Project Component and the Statement of Implementation of Loan Agreement of the financial statements is the responsibility of your entity, while the preparation of the Special Account Statement is the responsibility of Hunan provincial Finance Department, which includes:

1. Preparing and fair presenting the accompanying financial statements in accordance with Chinese accounting standards and system, and the requirements of the project loan agreement;

2. Designing, implementing and maintaining necessary internal control to ensure that the financial statements are free from material misstatement, whether due to fraud or error.

(II) Auditor’s responsibility

Our responsibility is to express an opinion on these financial statements based on our audit. We conducted our audit in accordance with the “Government Auditing Standards of the People’s Republic of China” and International Standards on Auditing. Those standards require that we comply with ethical requirements and plan and perform the audit to obtain reasonable assurance about whether the financial statements are free from material misstatement.

An audit involves performing procedures to obtain audit evidence about the amounts and disclosures in the financial statements. The procedures selected depend on the auditor’s judgment, including the assessment of the risks of material misstatement of the financial statements, whether due to fraud or error. In making those risk assessments, the auditor considers internal control relevant to the entities’ preparation and fair presentation of the financial statements in order to design audit procedures that are appropriate in the circumstances, but not for the purpose of expressing an opinion on the effectiveness of the entity’s internal control. An audit also includes evaluating the appropriateness of accounting policies used and the reasonableness of accounting estimates made by management, as well as evaluating the overall presentation of the financial statements.

We believe that the audit evidence we have obtained is appropriate and sufficient to provide a basis for our audit opinion.

(III) Opinion

In our opinion, the financial statements identified in the first paragraph present fairly, in all material respects, the financial position of Hunan Forest Restoration and Development Project financed by the World Bank as of December 31, 2019 and January to March, 2020, its financial receipts and disbursements, the project implementation and the receipts and disbursements of special account for the year then ended in accordance with Chinese accounting standards and system, and the requirements of the project loan agreement.

The audit report consists of the Auditor’s Opinion and two more parts hereinafter: financial statements and notes to the financial Statements, audit findings and recommendations.

Hunan Provincial Audit Office of the People’s Republic of China

June 24,2020

Address: No. 6 Jiayu Road,Changsha City, Hunan Province, P.R. China

Postcode: 410001

Tel.: (0731) 89976087

Fax: (0731) 89976085

（五）财务报表说明

财务报表说明

1、项目概况

根据中国政府和世界银行2013年3月签订的《贷款协定》，世行贷款湖南森林恢复和发展项目由世界银行提供8000万美元(按项目评估文件中确定的汇率1:6.25折合人民币5亿元)，中方资金人民币2.2亿元，概算总投资人民币7.2亿元。

2016年5月4日-11日，世行检查团对本项目进行了中期检查，并对项目进行了中期调整。根据备忘录确认，本项目由世界银行提供8000万美元(按备忘录中确定的汇率1：6.45折合人民币5.16亿元)，中方资金人民币2.1285亿元，总投资人民币7.2885亿元。

2、财务报表编制范围

本财务报表的报告数据包括湖南省项目办、湖南省森林植物园、22个县项目办的财务收支情况。

本报表数据期间为2019年1月1日至2020年3月31日。

3、主要会计政策

3.1会计核算基础：本项目会计核算按权责发生制进行，采用借贷复式记账法记账，以人民币为记账本位币。

3.2会计年度：会计年度为公历1月1日至12月31日。

3.3财务报表：项目执行单位按贷款协定要求为该项目设立了单独的账目，财务报表全面反映了世行贷款湖南森林恢复和发展项目经济活动。

4、报表有关科目说明

4.1在建工程

2019年度及2020年1--3月份的项目在建工程支出本期发生额为人民币11,057,159.18元，累计支出708,121,077.24，其中：

森林重建和恢复支出：本年度支出人民币4,183,208.79元，累计支出人民币655,878,153.43元。

机构支持与技术增强支出：本年度支出人民币6,873,950.39元，累计支出人民币50,993,772.41元。

4.2预付及应收款

2019年及2020年1--3月份的余额为人民币2,697,769.43元，主要是尚未办理完拨款手续的报账款、结余在财政专户的中方资金、预付项目工程的周转金等。

4.3 固定资产

2019年及2020年1--3月份的余额为人民币10,022,675.78元，为项目县自行购入的办公设备、项目经批准统一采购的设备以及苗圃升级形成的资产。

4.4项目拨款

22个项目县、省林业局外资办、省森林植物园财务报表数据汇总情况：截止2020年3月31日,项目拨款余额为人民币200,895,494.27元，其中：省级配套28,803,864.25元，县级配套401,29,154.35元，受益人投资131,962,475.67元。

4.5项目借款

截止2020年3月31日国外借款余额为人民币513,732,190.55元, 为向世界银行提取的项目贷款资金,其中:项目提款报账资金509,835,586.64元, 专用账户年末余额折人民币3,896,603.91元。

4.6应付款

2020年3月31日余额合计为人民币7,284,722.54元，主要是项目实施单位应支付的苗木费及劳务费。

4.7其他收入

2020年3月31日余额人民币38,085.60元，为项目单位银行存款利息收入。

4.8非流动资产基金

2020年3月31日余额为人民币10,022,675.78元，为固定资产的对应科目。

5、报表有关数据说明

5.1 本报告财务数据截止日为2020年3月31日。

5.2 本报告数据由宁乡县、醴陵市、耒阳市、常宁市、衡南县、新邵县、平江县、岳阳县、桃源县、鼎城区、汝城县、资兴市、苏仙区、桂东县、桂阳县、安仁县、永兴县、双牌县、金洞区、麻阳县、沅陵县、泸溪县、湖南省森林植物园、省项目办财务数据汇总而成。

5.3 专用账户数据

世行贷款湖南森林恢复和发展项目专用账户设在湖南省财政厅，由湖南省财政厅外经处管理。专用账户2019年及2020年1--3月份期初余额为2,564,137.64美元,本年世行回补0美元,利息收入495.49美元,本期支付2,008,502.49美元,结余556130.64美元（扣除利息净额13167美元，结余542,963.64美元）。

按财政部通知，以2018年12月28日美元兑人民币汇率1:6.8632折算，专用账户期初余额为人民币17,598,189.45元，按财政部通知，以2020年3月31日汇率1:7.0941折算,专用账户年末余额为人民币3945246.37元（扣除利息净额期末余额人民币3851838.36元）。

v. Notes to Financial Statements

Notes to Financial Statements

1.Project Overview

According to the Loan Agreement signed in March, 2013 between the Chinese government and the World Bank, Loans of the World Bank for Hunan Forest Restoration and Development Project were funded by the World Bank with USD 80 million (equivalent to RMB 500 million yuan, based on the exchange rate of 1:6.25 set by the project assessment documents) and China with RMB 220 million yuan. The overall investment was estimated to be RMB 720 million yuan.

From May 4 to 11, 2016, the World Bank inspection team carried out a mid-term review and adjustment to the project. According to the memorandum, the project was funded by the World Bank with USD 80 million (equivalent to RMB 516 million yuan, based on the exchange rate of 1:6.45 set by the memorandum) and China with RMB 212.85 million yuan. The overall investment was RMB 728.85 million yuan.

2.Scope of the Financial Statements

The financial statements consist of financial revenues and expenditures of Hunan Provincial Project Management Office (PPMO), Hunan Forest Botanical Garden and 22 counties in Hunan Province.

The financial statements are from January 1st, 2019 to March 31, 2020.

3.Principal Accounting Policies

3.1 Financial accruals basis: the accruals basis and debit/credit double-entry bookkeeping method are adopted. RMB is used as the recording currency of bookkeeping.

3.2 Fiscal year: the Gregorian Calendar year is adopted as the fiscal year from January 1st  to December 31.

3.3 Financial statements: the implementation entity sets separate accounts for the project in accordance with requirements of the loan agreement. The financial statements comprehensively demonstrate economic activities of Loans of the World Bank for Hunan Forest Restoration and Development Project.

4. Explanation of Subjects

4.1 Projects under Construction

In 2019 and January to March, 2020, expenditure of projects under construction was RMB 11,057,159.18 yuan, with accumulated expenditure amounting to RMB 708,121,077.24 yuan, including:

Expenditure of forest reforestation and rehabilitation: the expenditure of the current year was RMB 4,183,208.79 yuan, with accumulated expenditure amounting to RMB 655,878,153.43 yuan.

Expenditure of institution support and technical improvement: the expenditure of the current year was RMB 6,873,950.39 yuan, with accumulated expenditure amounting to RMB 50,993,772.41 yuan.

4.2 Prepayment and Account Receivable

The balance on 2019 and January to March, 2020 was RMB 2,697,769.43 yuan, mainly reimbursement funds not completing the disbursement procedure, surplus Chinese funds in the special financial account, and prepaid working funds of construction.

4.3 Fixed Asset

The balance on 2019 and January to March, 2020 was RMB 10,022,675.78 yuan, including assets from office facilities purchased by project counties, centrally purchased project facilities with approval, and nursery upgrade.

4.4 Project Disbursement

The financial statements of 22 counties in Hunan Province, Forestry Foreign Project Fund Management Office of Hunan Forestry Bureau, and Hunan Forest Botanical Garden are summarized as follows: the balance of project disbursement on March 31, 2020 was RMB 200,875,494.27 yuan, including: provincial counterpart funds of RMB 28,803,864.25 yuan, county counterpart funds of RMB 40,129,154.35 yuan and beneficiary investment of RMB 131,962,475.67 yuan.

4.5 Project Loans

The foreign loan balance - the project loan withdrawn from the World Bank - on March 31, 2020 was RMB 513,732,190.55 yuan, including withdrawal reimbursement of RMB 509,835,586.64 yuan and balance of special accounts at the end of year converted to RMB of 3,896,603.91 yuan.

4.6 Account Payable

The balance on March 31, 2020 was RMB 7,284,722.54 yuan, mainly payable nursery and labor costs of the implementation entity of the project.

4.7 Other Income

The balance on March 31, 2020 was RMB 38,085.60 yuan, deposit interest income of the project entity.

4.8 Illiquid Asset Funds

The balance on March 31, 2020 was RMB 10,022,675.78 yuan, mate accounts of fixed assets.

5. Notes to Statement Data

5.1 The financial statements dated up to March 31, 2020.

5.2 The report summarizes financial data from Ningxiang County, Liling City, Leiyang City, Changning City, Hennan County, Xinshao County, Pingjiang County, Yueyang County, Taoyuan County, Dingcheng District, Rucheng County, Zixing City, Suxian District, Guidong County, Guiyang County, Anren County, Yongxing County, Shuangpai County, Jindong District, Mayang County, Yuanling County, Luxi County, Hunan Forest Botanical Garden and Hunan PPMO.

5.3 Special Account Data

The special account of Loans of the World Bank for Hunan Forest Restoration and Development Project was opened in Hunan Provincial Department of Finance and managed by Foreign Economy and Trade Division of Hunan Provincial Department of Finance. As for the special account, the balance at the beginning of the period in 2019 and January to March, 2020 was USD 2,564,137.64, the replenishment of the World Bank of the current year was USD 0, the interest income was USD 495.49, the disbursement of the current period was USD 2,008,502.49, and the surplus was USD 556,130.64 (after deducting the net interest of USD 13,167, and the balance was USD 542,963.64).

The balance at the beginning of the period was RMB 17,598,189.45 yuan, based on the USD/RMB exchange rate of 1:6.8632 announced by Ministry of Finance of the People’s Republic of China on December 28 , 2018. The balance at the end of the period was RMB 3,945,246.37 yuan  (after deducting the net interest, and the balance at the end of the period was USD 3,851,838.36), based on USD/RMB exchange rate of 1:7.0941 announced by Ministry of Finance of the People’s Republic of China on March 31, 2020.

三、审计发现的问题及建议

审计发现的问题及建议

除对财务报表进行审计并发表审计意见外，审计中我们还关注了项目执行过程中相关单位国家法规和项目贷款协定遵守情况、内部控制和项目管理情况、项目绩效以及上一年度审计建议整改落实情况。该项目首次在湖南把生态林建设作为项目的主要目标和建设内容，目的明确，具有一定的前瞻性；项目实施方式灵活多样，采取了国营林场、造林大户、林业专业合作社组织、村集体等多种实施模式，满足了各阶层主体的需求，提高了各相关实施主体参与项目的积极性。但我们发现还存在如下问题：

（一）项目管理方面存在的问题

项目区未设立永久性标志。

审计抽查发现常德市鼎城区等地均存在除示范林项目外，其他项目未按世行要求设立标志牌的问题。

上述做法不符合《世界银行贷款湖南森林恢复和发展项目管理办法》（湘林外资【2013】41号）第四款第九条“项目区应设立永久性标志。工程牌应设置在本县主体工程靠近主要交通干道的醒目位置。工程牌式样按省项目办统一要求设置。”的规定。建议你办依照《世界银行贷款湖南森林恢复和发展项目管理办法》要求，督促相关县项目办设置统一要求的工程牌式。你办已接受审计建议。

（二）固定资产管理不规范

固定资产采购未严格履行程序，固定资产移交、管理和使用欠规范。

现场抽查汝城林业外资项目管理办公室时发现，汝城县项目办办公设备采购、管理和使用不合规，涉及电脑等设备共计9.47万元。其中:省项目办2014年分配的7台电脑等计4.22万元，主要在机关各股室使用，1台笔记本电脑在县财政局外经股使用，至审计之日仍未收回,;2018年自行采购的16台平板电脑共计5.25万元，没有采购合同，也未履行政府采购目录的相关程序。自行采购的16台平板电脑4台在机关营林站，12台在下属12个林业工作站。

现场抽查泸溪县林业外资项目管理办公室固定资产台账，发现未按“一卡一物一条码”等管理要求登记品牌、规格型号等；在2019年泸溪县林业局与自然资源局机构改革合并时未办理固定资产移交手续，也没有领用人签名，且部分固定资产未用于世行项目，不符合相关要求。

上述做法不符合湖南省财政厅关于印发《湖南省2018年省级政府集中采购目录及政府采购限额标准》的通知（湘财购〔2018〕2号）第五条（一）“各级国家机关、事业单位和团体组织使用财政性资金，采购集中采购目录以内或者采购限额标准以上的货物、服务和工程类项目，必须执行政府采购制度……” 和《行政单位国有资产管理暂行办法》（财政部令第35号）第二十条“行政单位对所占有、使用的国有资产应当定期清查盘点，做到家底清楚，账、卡、实相符，防止国有资产流失”、《事业单位国有资产管理暂行办法》（中华人民共和国财政部令第36号）第二十条“……事业单位应当对实物资产进行定期清查，做到账账、账卡、账实相符……”等规定。

建议你办并督促各项目县（市、区）林业外资项目管理办公室按照有关规定和《省财政厅关于开展2016年全省行政事业单位国有资产清查工作的通知》、《行政单位国有资产管理暂行办法》（财政部令第35号）有关要求，对外资项目固定资产按要求执行政府采购制度，建立健全账卡制度，完善资产管理信息，实行“一物一卡一条码”管理，切实做到账表、账账、账卡、账实相符。你办已接受审计建议。

（三）上一年度审计发现问题未整改情况

审计发现，上一年度审计报告中披露的问题中，项目区未设置永久性标志的问题有的项目区未整改到位，本年度仍然存在。

建议你办并督促各项目县（市、区）林业外资项目管理办公室切实制定和落实整改措施，完善制度，加强项目管理。你办已接受审计建议。

# Ⅲ Audit Findings and Recommendations

Audit Findings and Recommendations

In addition to performing the audit and expressing an opinion on the financial statements, we also make observations with respect to compliance with applicable provisions of state laws and regulations and the loan agreement of the relevant entities, its internal financial control and project management, project performance and the follow-up of previous recommendations during the project implementing process. The project puts plantation of ecological forest as the main objective and construction content, with a clear purpose and certain perspective; the project features flexible modes of implementation, which includes involvement of state-own forest farms, major forestation entities, specialized cooperatives of forestry and village collectives, therefore fulfilling requirements of entities of all classes and enhancing initiatives of implementation entities. However, we still found some problems as follows:

(I) Issues of project management

No permanent signs in project spots.

Spot checks found that except for demonstration forests, no signboards were built in accordance with standards of the World Bank in other projects of Dingcheng District, Changde City and other places.

The aforementioned practices violated “permanent signs shall be built in project spots. Construction signs shall be built in highlighted locations near to main roads in the main construction site. Construction signs shall be designed in accordance with uniform requirements of Hunan Provincial Project Office”, Paragraph Nine, Article Four of Measures for Loans of the World Bank for Hunan Forest Restoration and Development Project（Xianglinwaizi No. 41 [2013]）.We recommend you urge relevant county project offices to build unified construction signs in accordance with Measures for Loans of the World Bank for Hunan Forest Restoration and Development Project. You have accepted our recommendations.

(II) Non-standard management of fixed assets

Procedures were not strictly obeyed in fixed assets procurement, and transfer, management and use of fixed assets were non-standard.

Spot checks of in Rucheng County Forestry Foreign Fund Project Management Office found irrational procurement, management and use of office facilities such as computers, totaled 94.7 thousand yuan in Rucheng County project office. Among which: 7 computers, with a total value of 42.2 thousand yuan, allocated from the provincial project management office in 2014, were mainly used in sections and divisions of the administrative institution, and 1 laptop was used in the foreign fund section of the county financial bureau, which were still not taken back by the date of audit. There were no procurement contracts and no execution of related government procurement catalog procedures for 16 voluntarily procured tablet computers in 2018, amounting to 52.5 thousand yuan. Of the voluntarily procured 16 tablet computers, 4 were in the afforestation station of the administrative institution, and 12 were in 12 subordinate forest stations.

Spot checks of the fixed assets standing book of Luxi County Forestry Foreign Fund Project Management Office found that registration of brand, specification and type, etc. were not executed in conformity with the management requirement of “one card, one facility and one bar-code”. During the institutional reform and combination between Luxi County Forest Bureau and Natural Recourse Bureau in 2019, there was no execution of transfer procedures for fixed assets nor signature of recipient, in addition, some fixed assets were not used for the World Bank Project, which was not in conformity with relevant requirements.
The aforementioned practices violated stipulations such as “administrative institutions, in procurement of assets included in the government procurement scope, should go through government procurement according to laws”, Article Sixteen of Interim Measures of National Assets Management in Administrative Institutions, “procurement of vehicles and office facilities should be strictly controlled...”, Article Twenty-three of Interim Measures for Financial Management of Loan and Grant Projects of International Financial Institutions (Caiji No. 10 [2011]) and “national institutions, public institutions, organizations and groups , in procurement through usage of financial funds of cargoes, service and projects included in the central procurement catalog or beyond the quota , must go through the government procurement mechanism...”, Article Five (I) of Provincial Government Centralized Procurement Catalog and Government Procurement Quota Standard of Hunan Province, 2018 (Xiangcaigou No. 2 [2018]). The aforementioned practices also violated “administrative institutions shall take regular inventory of the state-owned assets they possess and use, ensure a clear picture of the total assets and consistency of ledgers, cards and facilities, and prevent loss of state-owned assets”, Article Twenty of Interim Measures for State-owned Assets Management of Administrative Institutions (Order No. 35 of the Ministry of Finance), “...public institutions shall take regular inventory of the state-owned assets they possess and use, so as to ensure consistency of ledgers, cards and facilities, ...”, Article Twenty of Interim Measures for the State-owned Assets Management of Public Institutions (Order No. 36 of the Ministry of Finance), and other related regulations.

We recommend you and urge all relevant county (city, district) forestry foreign fund project management offices, based on requirements of Notice of Hunan Provincial Department of Finance on Inventory of State-owned Assets in Provincial Administrative and Public Institutions in 2016 and Interim Measures for State-owned Assets Management of Administrative Institutions (Order No. 35 of the Ministry of Finance) to take inventory of fixed-assets of foreign funded projects, set up and improve the system of ledger and card, take management of asset  information, and manage ledgers in accordance with "one card, one facility and one bar-code" requirement, so as to ensure consistency in ledgers, tables, cards and facilities. You have accepted our recommendations.

(III) The Followed-up of previous recommendations

We found some audit findings this year, i.e. no permanent signs in project spots, disclosed in the audit report of the previous year were still not followed up.

We recommend you urge all relevant project counties (cities, districts) to take practical follow-up measures, improve the system, and strengthen the management to promote project smooth implementation. You have accepted our recommendations.